## Sheet1
Sprint 1
| Burned Down |  | Balance |  | Daily Completed
Day | Estimate | Actual | Estimate | Actual
1 | 0 | 0 | 240 | 240 | 0
2 | 12 | 16 | 228 | 224 | 16
3 | 6 | 10 | 222 | 214 | 10 | Member per team = 4 person
4 | 8 | 20 | 214 | 194 | 20 | Work hour perday = 4h
5 | 10 | 16 | 204 | 178 | 16 | Work day per week = 5 day
6 | 6 | 12 | 198 | 166 | 12 | Week per sprint = 3 weeks
7 | 4 | 4 | 194 | 162 | 4 | Available = 240
8 | 4 | 8 | 190 | 154 | 8
9 | 8 | 12 | 182 | 142 | 12
10 | 25 | 16 | 157 | 126 | 16
11 | 30 | 16 | 127 | 110 | 16
12 | 8 | 10 | 119 | 100 | 10
13 | 8 | 8 | 111 | 92 | 8
14 | 4 | 10 | 107 | 82 | 10
15 | 4 | 12 | 103 | 70 | 12
16 | 10 | 12 | 93 | 58 | 12
17 | 10 | 10 | 83 | 48 | 10
18 | 7 | 7 | 76 | 41 | 7
19 | 26 | 16 | 50 | 25 | 16
20 | 30 | 16 | 20 | 9 | 16
21 | 20 | 9 | 0 | 0 | 9

## Sheet2
**Product UI/UX Design:** | Estimated
1. Conduct user interviews to gather insights on user preferences and pain points. | 12
2. Create user personas based on the collected data to represent different user segments. | 6
3. Sketch initial wireframes on paper or using digital tools to visualize the basic layout and flow. | 8
4. Design high-fidelity mockups using design software like Sketch or Figma, incorporating branding elements and visual styles. | 10
5. Conduct usability testing with a sample group of users to gather feedback on the design and iterate accordingly. | 6
1. Research HRM website competitors to analyze their features and functionalities. | 4
2. Define user stories and create a backlog of features based on stakeholder requirements. | 4
3. Develop a sitemap to organize the structure and navigation of the website. | 8
4. Design and implement a responsive front-end using HTML, CSS, and JavaScript frameworks. | 25
5. Set up a back-end system to handle user authentication, database interactions, and business logic using technologies like Node.js or Django. | 30
1. Identify and prioritize the key entities in the HR domain, such as employees, departments, and positions. | 8
2. Create an entity-relationship diagram (ERD) to visualize the relationships between different entities. | 8
3. Define the attributes and data types for each entity based on the information to be stored. | 4
4. Normalize the database schema to eliminate redundancy and minimize data anomalies. | 4
5. Review and optimize the schema design for performance and scalability, considering factors like indexing and query optimization. | 10
1. Gather requirements from managers and stakeholders to understand their needs and expectations. | 10
2. Create user stories or use cases to document the desired functionality of the portal. | 7
3. Design a user-friendly interface with intuitive navigation and clear calls-to-action. | 26
4. Develop features such as employee performance dashboards, task management tools, and reporting capabilities. | 30
5. Implement role-based access control to ensure that managers only have access to relevant data and functionality. | 20